## Sheet1
This spreadsheet is meant to track progress of an FRI's final stages of preparation | Value
Unit name and year: | English River 2015
original GDB or Shapefile name from contractor: | This unit was a merge of work from three contractors - KBM/GFMI/Enfor
Contractor contact: | KBM / GFMI / Enfor
Attributes
1) Seamless received on | 10/12/2015 - last piece received
2) Correct Projection? | UTM Z15 NAD83
3) POLYIDs unique? | Yes - after finding 122 duplicates and fixing them by adding a,b,c etc as suffix
4) All attributes present and properly defined? | Yes
5) All attributes within range or have valid values? | Yes
6) Fim Attribute Check version:
7) Fim Attribute Check run? (Number Errors?) | 0
8) Fim Attribute Check run? (Number Warnings?) | 1493
Topology
9) FRI totally covers Project Area? | no - due to interp only being done to Caribou and Wabakimi existing Interp and new water edge
10) Overlaps? | 5 - gaps that exist exterior to the project boundary
11) Gaps? | 0
12) Ensure fit with adjoining units already completed | Yes this unit fits the Caribou and Wabakimi - for most of the shared length of these units a railline separates the two project boundaries. Where forest ties to forest the vertices are a match.
13) Calibration Plots Checked? | Yes - completed by Enfor
Additional Checks
14) Adhoc Expression Checks Run? | Yes
15) Overlay with Supplemental Info done? | Yes
16) Comment file made to document unique cases?
17) Date loaded to LIO Warehouse: | May 11th, 2016
18) Final GDB name | pp_FRI_FIMv2_EnglishRiver_(230)_(2013)_2D.gdb