## Sheet1
This spreadsheet is meant to track progress of an FRI's final stages of preparation | Value
Unit name and year: | Ogoki 2010
original GDB or Shapefile name from contractor: | Downloaded from LIO to upgrade OSC and MGMTCONs
Contractor contact: | Teco/Sumac
Attributes
1) Seamless received on | February 3rd, 2016 from LIO Website
2) Correct Projection? | Yes - NAD83 Z16
3) POLYIDs unique? | Yes
4) All attributes present and properly defined? | Yes
5) All attributes within range or have valid values? | Yes
6) Fim Attribute Check version:
7) Fim Attribute Check run? (Number Errors?)
8) Fim Attribute Check run? (Number Warnings?)
Topology
9) FRI totally covers Project Area? | Yes
10) Overlaps? | 0
11) Gaps? | 6 - one of which was an uncoded ISLD = POLYID 653649229 - all remaining gaps are uncoded sections outside of MU
12) Ensure fit with adjoining units already completed | Yes
13) Calibration Plots Checked? | Yes
Additional Checks
Ran update for OSC values and updated MGMTCON1 and MGMTCON2 to reflect WETT Ecosites to overwrite values of NONE - otherwise leave alone
14) Adhoc Expression Checks Run? | Not run as the unit is already into production cycle
15) Overlay with Supplemental Info done? | Not run as the unit is already into production cycle
16) Comment file made to document unique cases? | No
17) Date loaded to LIO Warehouse: | 2016-02-11
18) Final GDB name | pp_FRI_FIMv2_OgokiForest_(796)_2010_2D.gdb